Library Services to People with Special Needs

# IFLA Working Group on Prison Libraries

Action Plan 2019 – 2023

IFLA Section on Libraries

for Persons with Special Needs (LSN)

June 2022

# Major project outcomes:

# - Updated IFLA Guidelines for Prison Libraries

# - Preparation of the session on prison libraries at IFLA WLIC 2022 in Dublin

# - Content management of the IFLA LSN project page on prison libraries

# - Input provided for a UNESCO policy brief on prison libraries

Current Working Group members:

Chair:		Lisa Krolak, UNESCO Institute for Lifelong Learning, Hamburg, Germany

Co-Chairs:	Gerhard Peschers, JVA (Prison) Münster, Germany

Samira Zahra, Goethe-Institut Bulgaria, Sofia

Additionally, about 45 members from all regions of the world.

| What | Who | When |
| --- | --- | --- |
| Meeting of Working Group | Chairs | 28 August 2019 IFLA WLIC Athens, Greece |
| Establishing a LSN project page on prison libraries | Marie Eiriksson, Information Officer, LSN | October 2019 |
| Locating members for the Working Group | Chairs and Working Group | ongoing |
| Compilation of a background reading list on prison libraries for the project page on prison libraries | Lisa Krolak and Working Group | January – April 2020 ongoing |
| Providing input for a UNESCO policy brief on prison libraries | Lisa Krolak and Working Group | January/February 2020 |
| Compilation of a list with working tools for prison libraries for the project page on prison libraries | Lisa Krolak and Working Group | Summer 2020 ongoing |
| Establishment and maintenance of a Listserv for the global prison library community | Lisa Krolak | July 2020 |
| Updating the IFLA Guidelines for Prison Libraries (first virtual meetings in March, April and May) | Jane Garner Guidelines Working Group | March 2021 – Summer 2022 |
| Meeting of the Guidelines Working Group to present the first full draft, during the virtual IFLA WLIC 2021 in Rotterdam, Netherlands (19 – 26 August 2021) | Jane Garner Guidelines Working Group | 23 August 2021 IFLA WLIC Rotterdam |
| Meeting of the Guidelines Working Group to discuss proposed changes to the first full draft | Jane Garner Guidelines Working Group | 20 September 2021 |
| Final draft of the Guidelines shared with global prison library community, LSN section and via IFLA Listserv and IFLA newsletter for comments | Jane Garner | 15 February 2022 |
| Guidelines shared with IFLA for comments | Jane Garner Lisa Krolak | May – June 2022 |
| Session on prison libraries during IFLA 2022 in Dublin, Ireland: - Presenting the new IFLA Guidelines for Prison Libraries - Presentation of best practice examples | Working Group Guidelines Working Group LSN Section | 27 July 2022 IFLA WLIC Dublin 26 – 29 July 2022 |
| Meeting of the Working Group | Working Group | IFLA WLIC 2022 |
| Translation of the updated Guidelines into other languages | Working Group | ongoing |
| Meeting of the Working Group to assess impact | Working Group | IFLA WLIC 2023 Rotterdam |